## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Other coursework interrupts project schedule. | 20 | 70 | 1400 | 2021-03-18 | Mitigated | M | Stay up later or delay other coursework in an attempt to stay on schedule.
Need to work extra hours for job. | 3 | 8 | 24 | 2021-03-18 | Accept | A | Accept time lost.
Cannot solve unforseen bug. | 70 | 70 | 4900 | 2021-03-18 | Resolve | R | Speak to TA during office hour or send message on slack.
Computer Malfunctions, Project Data is lost | 3 | 3 | 9 | 2021-03-18 | Mitigated | M | Store local files to clouds storage.
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100